## PRODUCT BACKLOG
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
04/11/2024 - 10/11/2024 | 04/11/2024 - 10/11/2024 | US001 | Set up database structure | Must Have | None |  | Completed
04/11/2024 - 05/11/2024 | 04/11/2024 - 05/11/2024 | US002 | Create wireframe for UI | Should Have | US001 |  | In Progress
06/11/2024 - 07/11/2024 | 06/11/2024 - 07/11/2024 | US003 | Research for symptom database | Could Have | None |  | Not Started
08/11/2024 - 09/11/2024 | 08/11/2024 - 09/11/2024 | US004 | Train AI model with symptoms | Must Have | US003 |  | Not Started
2024-10-11 | 2024-10-11 | US005 | Test basic application setup | Should Have | US001 |  | Not Started

## SPRINT BACKLOG
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US001 | T001 | Set up database structure | 2024-04-11 | 2024-04-11 | Backend Team | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US002 | T002 | Create wireframe for UI | 2024-04-11 | 2024-05-11 | UI/UX Team | Design | In Progress | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US003 | T003 | Research for symptom database | 2024-06-11 | 2024-07-11 | Data Team | Research | Not Started | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US004 | T004 | Train AI model with symptoms | 2024-08-11 | 2024-09-11 | AI Team | Training | Not Started | 10 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US005 | T005 | Test basic application setup | 2024-10-11 | 2024-10-11 | QA Team | Testing | Not Started | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## STANDUP MEETING
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2024-05-11 | Environment setup delayed | Fixed with IT team support.
Sprint 2 | 20/11/2024 | Missing data for symptom research | Asked medical experts for inputs.
Sprint 3 | 2024-02-12 | UI/UX team unavailable | Reassigned tasks to backup team.
Sprint 4 | 17/12/2024 | AI training slow | Optimized data and resources.

## RETROSPECTION
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2024-04-11 | 17/11/2024 |  | Prioritize daily stand-ups | Delaying task updates | Regular progress tracking | Set clear deadlines for tasks
2 | Sprint 2 | 18/11/2024 | 2024-01-12 |  | Regular dependency checks | Ignoring blockers | Collaborating for issue fixes | Create dependency tracking sheet
3 | Sprint 3 | 2024-02-12 | 15/12/2024 |  | Document task progress | Skipping documentation | Maintaining communication logs | Use shared documentation tools
4 | Sprint 4 | 16/12/2024 | 27/12/2024 |  | Focus on sprint reviews | Ignoring retrospectives | Continuous feedback collection | Schedule regular sprint reviews